## Feuil1
Environment Backlog | SPRINT 1: 20-30 sept | SPRINT 2: 2-14 oct | SPRINT 3: 14-28 oct | SPRINT 4: 28-11 nov | SPRINT 5: 11-20 nov | SPRINT 6: 20-2 dec | SPRINT 7: 2-10 dec | Faites Par
[9 empty] | Abandonné | Fini | En cours | à faire
Static Mesh
SM_arche_redesign |  |  |  | x |  |  |  | Michael
SM_panneau_redesign |  |  |  | x |  |  |  | Michael
SM/SK_vaiseau_silouettes/design_01 | x | [6 empty] | julien
SM/SK_vaiseau_silouettes/design_02 | x | [6 empty] | julien
SM/SK_vaiseau_silouettes/design_03 | x | [6 empty] | julien
SM/SK_vaiseau_silouettes/design_04 | x | [6 empty] | julien
SM/SK_vaiseau_silouettes/design_05 |  | x | [5 empty] | julien
SM/SK_vaiseau_silouettes/design_06 |  | x | [5 empty] | julien
SM/SK_vaiseau_vagon1 |  | x | x |  |  |  |  | julien
SM/SK_vaiseau_vagon2 |  |  | x | x |  |  |  | julien
SM/SK_vaiseau_vagon3 |  |  | x | x |  |  |  | julien
SM/SK_vaiseau_redisign_01 |  |  |  | x |  |  |  | julien
SM/SK_vaiseau_redisign_02 |  |  |  |  | x |  |  | julien
SM/SK_vaiseau_2vagons_cannés | [5 empty] | x |  | julien
SM/SK_vaiseau_redisign_03 | [5 empty] | x |  | julien
SM_Paserelles_Supports |  |  | x | x | x |  |  | marc-antoine
SM_echafaudage_X P3
SM_Eechafaudage_ecaire P3
SM_silo_01 P3
SM_silo_02 P3
SM_silo_base P3
SM_purgeur P3 | [5 empty] | x |  | fred
SM_vegetation_clutter_01 |  | x | [5 empty] | marc-antoine
SM_vegetation_clutter_02 |  | x | [5 empty] | marc-antoine
SM_vegetation_clutter_03 |  | x | [5 empty] | marc-antoine
SM_vegetation_clutter_04 |  | x | [5 empty] | marc-antoine
SM_vegetation_clutter_05 |  | x | [5 empty] | marc-antoine
SM_vegetation_clutter_06 |  | x | [5 empty] | marc-antoine
SM_vegetation_moyenne_01 |  |  | x |  |  |  |  | michael
SM_vegetation_moyenne_02 P3 | [5 empty] | x |  | gab
SM_crystaux_Petits (4) | [5 empty] | x |  | Jonathan
SM_crystal_moyenne |  |  | x |  |  |  |  | Jonathan/fred
SM_crystal_grand |  |  | x |  |  |  |  | Jonathan/fred
SM_Stalagmite_01 |  |  | x |  |  |  |  | michael
SM_stalagmite_02 P3
SM_stalagmite_colonne P3
SM_vegetation_grande_01 |  |  | x | x | x |  |  | gab
SM_vegetation_grande_02 |  |  | x | x | x |  |  | gab
SM_vegetation_grande_02 |  |  | x | x | x |  |  | gab
SM_vegetation_grande_02 |  |  | x | x | x |  |  | gab
SM_roche_moyenne_01 | x | [6 empty] | fred
SM_roche_moyenne_02 | x | [6 empty] | fred
SM_roche_moyenne_03 | x | [6 empty] | fred
SM_roche_moyenne_04 | x | [6 empty] | fred
SM_roche_moyenne_05 |  | x | [5 empty] | michael
SM_roche_moyenne_06 |  | x | [5 empty] | michael
SM_roche_moyenne_07 |  | x | [5 empty] | michael
SM_roche_grande_01 | x | [6 empty] | fred
SM_roche_grande_02 |  | x | [5 empty] | michael
SM_roche_grande_03 |  | x | [5 empty] | michael
SM_roche_grande_04
SM_roche_grande_05
SM_roche_petite_01 | x | [6 empty] | fred
SM_roche_petite_02 | x | [6 empty] | fred
SM_roche_petite_03 | x | [6 empty] | fred
SM_roche_petite_04
SM_roche_petite_05
SM_roche_arche | x | [6 empty] | fred
SM_arche | x | [6 empty] | michael
SM_panneau |  | x | [5 empty] | michael
SM_tuyaux_modulaire | x | [6 empty] | fred
SM_landscape | x | [6 empty] | fred / marc-antoine
SM_beam | x | [6 empty] | fred
SM_lampe |  |  | x |  |  |  |  | fred
SM_pillier_arche | x | x | [5 empty] | gab
SM_outpost (all props included) |  | x | x | x | x |  |  | marc-antoine
SM_passerelles_01 |  |  | x | x | x |  |  | marc-antoine
SM_passerelles_02 |  |  | x | x | x |  |  | marc-antoine
SM_passerelles_03 |  |  | x | x | x |  |  | marc-antoine
SM_passerelles_04 |  |  | x | x | x |  |  | marc-antoine
SM_passerelles_05 |  |  | x | x | x |  |  | marc-antoine
SM_roche_concave_01 |  |  | x |  |  |  |  | michael
SM_roche_concave_02
SM_roche_concave_03
SM_plateform_propulsee |  |  | x |  |  |  |  | greg
SM_skybox |  |  | x | x | x |  |  | fred
SM_roche_falaise |  |  | x |  |  |  |  | michael
SM_immeuble_01 |  |  | x |  |  |  |  | fred
SM_immeuble_02 |  |  | x |  |  |  |  | fred
SM_immeuble_03 |  |  | x |  |  |  |  | fred
Paintover (concept) |  |  |  | x |  |  |  | fred
SM_roche_0x |  |  |  | x | x |  |  | fred/gab/Joe
SM_roche_0x |  |  |  | x | x |  |  | fred/gab/Joe
SM_roche_0x |  |  |  | x | x |  |  | fred/gab/Joe
SM_roche_0x |  |  |  | x | x |  |  | fred/gab/Joe
SM_roche_0x |  |  |  | x | x |  |  | fred/gab/Joe
SM_roche_0x |  |  |  | x | x |  |  | fred/gab
SM_montagne_0x |  |  |  | x | x |  |  | fred/gab
SM_montagne_0x |  |  |  | x | x |  |  | fred/gab
SM_montagne_0x |  |  |  | x | x |  |  | fred/gab
Landscape(redesign) |  |  |  | x | x |  |  | michael
LOD (1,2,3) sur Les roches |  |  |  |  | x |  |  | Fred
SM_skysphere_Version_02 |  |  |  |  | x |  |  | Fred
Outpost_blocking |  |  | x |  |  |  |  | greg
Plateforme_propulsée |  |  | x |  |  |  |  | greg
Collision for insta death
SM_roche1 | [5 empty] | x |  | michael
SM_roche2 | [5 empty] | x |  | michael
SM_mountain_01 | [5 empty] | x |  | michael
SM_mountain_02 | [5 empty] | x |  | michael
SM_roche_falaise_01 | [5 empty] | x |  | michael
SM_roche_falaise_02 | [5 empty] | x |  | michael
SM_roche_pointue_01 | [5 empty] | x |  | michael
SM_roche_sol_01 | [5 empty] | x |  | michael
Colour palet
tweak overall colours | [6 empty] | x | michael/fred
Pause menu / Interface
Buttons | [6 empty] | x | michael
splash screen | [6 empty] | x | michael/Fred
HUD | [6 empty] | x | Jonathan
Optimization
Grass clutter x 6 | [5 empty] | x |  | michael/fred
Arch support | [5 empty] | x |  | michael
aArch front pannels | [5 empty] | x |  | michael
Pannel | [5 empty] | x |  | michael
Cactus | [5 empty] | x |  | michael
pipelines
ship | [6 empty] | x | julien
trees | [5 empty] | x |  | gab
textures : 36 maps downsizés | [6 empty] | x | Fred
SM_mountain_01 (topo -80%) | [5 empty] | x |  | Fred
Textures : 22 Maps downsizés | [6 empty] | x | Fred
Troubleshooting Build Errors
Landscape | [5 empty] | x |  | michael / Fred
M_metal_01 (failed to load) | [5 empty] | x |  | michael
working build troubleshoot (20h) | [5 empty] | x |  | fred/michael/patrice
troubleshoot (lights) (10h) | [6 empty] | x | Fred
Tests de Performance (3 Builds consecutifs) | [6 empty] | x | Fred
Materiels / shaders / textures
M_calcaire
S_eau | [7 empty] | Gab
S_chute | [7 empty] | Sebastien
M_landscape_roche | x | [6 empty] | fred
MF_stalagmite_eau
M_landscape_falaise | x | [6 empty] | fred
M_landscape_mousse | x | [6 empty] | fred
S_beam | x | [6 empty] | fred
M_metal_01 | x | [6 empty] | michael
MF_metal_01 | x | [6 empty] | michael
M_metal_scifi_01 | x | [6 empty] | michael
MF_metal_scifi_01 | x | [6 empty] | michael
M_sable (landscape&VP) |  |  |  | x | x |  |  | fred
M_skybox |  |  | x | x | x |  |  | fred
MF_skybox |  |  | x | x | x |  |  | fred
MF_vertex_displacement |  | x | [5 empty] | michael
M_opacity_holemap |  | x | [5 empty] | michael
M_roche_grotte |  |  | x |  |  |  |  | michael
M_roche(landscape & VP) |  |  |  | x |  |  |  | Michael
M_roche_02 (landscape & VP) |  |  |  | x |  |  |  | Michael
M_mouse (landscape & VP) |  |  |  | x |  |  |  | Michael
M_eau |  |  |  |  | x
M_landscape_Version_02 Sol |  |  |  |  | x |  |  | Fred
M_skybox_Version_02 |  |  |  |  | X |  |  | Fred
M_Shockwave (Ajustement et implementation) | [6 empty] | x | Fred
M_drift_dash | [6 empty] | x | Fred
Ajustement des 6 Materiaux du vaisseau | [6 empty] | x | Fred
Ajustement des 3 Materiaux des Crystaux | [6 empty] | x | Fred
Correction Du Self Ilu (arches) | [6 empty] | x | Fred
M_Outpost_Sol |  |  |  | x | x | x | x | marc antoine
M_Outpost_Batiment |  |  |  | x | x | x | x | marc antoine
M_Clutter |  | x | x | x | x | x | x | marc antoine
M_metal_ship_01 |  |  |  | x | x |  |  | julien
M_metal_ship_02 |  |  |  | x | x |  |  | julien
M_metal_ship_03 | [6 empty] | x | julien
M_Slides_ship_01 |  |  |  | x | x |  |  | julien
M_grillage_ship_01 |  |  |  | x | x |  |  | julien
M_decals_ship_01 |  |  |  | x | x |  |  | julien
M_bloom_ship_01 | [6 empty] | x | julien
M_bloom_ship_02 | [6 empty] | x | julien
M_metal_ship_tweak_01 | [6 empty] | x | julien
M_metal_tweak_ship_02 | [6 empty] | x | julien
Particle effects
PE_chute_splash | [7 empty] | Gab
PE_chute_mist
PE_montagne_sable | [5 empty] | x | x | gab
PE_panneau_activation |  |  |  | x |  |  |  | seb
splash on visor | [6 empty] | x | gab
shockwave | [6 empty] | x | walid
air particles | [6 empty] | x | walid
Lightpass
Priliminary light pass | x | [6 empty] | fred
Intrum light pass |  | x | [5 empty] | fred
light pass (Beta) |  |  |  | x |  |  |  | Fred
light pass (GOLD) (4 passes) |  |  |  |  | x | x | x | fred/michael
Animations
SK_panneau_acivation |  | x | [5 empty] | michael
SK_panneau_activation_redesign |  |  |  | x |  |  |  | Michael
SK_ship_rotation_piece |  |  |  | x |  |  |  | julien
Level Art
First playable | x | [6 empty] | walid / michael / fred
ALPHA |  | x | x |  |  |  |  | walid / michael
BETA |  |  |  | x | x |  |  | michael/julien/M-A/greg
GOLD | [5 empty] | x | x | michael/M-A/julien/nick(nest)/greg
Correction de la spline | [6 empty] | x | Fred/greg
Production du Trailer
enregistrement du gameplay | [6 empty] | x | Walid/Michael/Fred
Montage/son | [6 empty] | x | Fred